## EITI Work Plan 2024
No | Objectives | Activities | Outcomes | Responsible Parties | 2024 |  |  | Semester I - 2024 | [23 empty] | Semester II - 2024
[7 empty] | Funding Resources | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
[5 empty] | Timeline | Cost (IDR) |  | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV
1 | Monitoring & Evaluation Strengthen active participation and collaboration between MSG stakeholders (government, companies, and civil society) and the public to contribute to policy making regarding extractive industry governance.
| a. EITI Validation | Response to the results of the 2024 EITI validation initial assessment | Coordinating with MSG to provide input on the results of the 2024 EITI validation assessment | MSG with National Secretariat support | 2024-03-01 | 119000000 | Government Budget | bar: March II
| b. MSG Stakeholder Consultation | MSG Meeting EITI Indonesia 1 | Increased understanding of MSG members regarding their roles and responsibilities; clear procedures for nominationsMSG Member; Active participation of MSG members and collaboration between them in EITI Indonesia activities | MSG with National Secretariat support | 2024-07-01 | 173000000 | Government Budget | bar: July II
|  | MSG Meeting EITI Indonesia 2 |  | MSG with National Secretariat support | 2024-12-01 | 120000000 | Government Budget | bar: December I
2 | Updating Data Portal Contribute to improving the investment climate by providing open-format data and improving corruption prevention through extractive data portals so as to increase disclosure of extractive industry governance data.
| a. Updating contextual narration and extractive data in the Portal | Technical Coordination about Tax & Non Tax Revenue from O&G and Coal & Minerals Sector (Req 4.1, 4.2, 4.7, 4.9) | Collaboration with units related to tax data and non-tax state revenues through data collection or data integration to update contextual narratives and data on the extractive industry data portal in 2022 and 2023 | MSG , National Secretariat |  | 40000000 | Government Budget | bar: April I; June III; August IV
|  | Technical Coordination about License Allocation (Req 2.2) and License Register (Req 2.3) | Collaborate with units related to permit allocation data and permit lists to update permit allocation mechanisms, transfer oil and gas and mineral and coal sector permits, and obtain permit application dates on the extractive data portal. | MSG , National Secretariat |  | 22570000 | Government Budget | bar: March III; July III
|  | Technical Coordination about Production Data from O&G and Coal & Minerals Sector (Req 3.2) | Collaboration with units related to production data to fulfill EITI standards on the extractive data portal | MSG , National Secretariat |  | 22000000 | Government Budget | bar: May II; August I
|  | Technical Coordination about Export Data (Req 3.3) and Economic Contribution (Req 6.3) | Collaboration with units related to export data and economic contribution to fulfill EITI standards on the extractive data portal | MSG , National Secretariat |  | 22000000 | Government Budget | bar: May I; August II
|  | Technical Coordination about State of Participation BUMN (Req 2.6), Transactions Related to State-Owned Enterprises (Req 4.5), Quasi-Fiscal Expenditure (Req 6.2) | Collaboration with data related units Information regarding transfers from the government to BUMN from the cash flow report, under "Funding Activities". Transfers from the government to BUMN and the consolidated financial statements present the value of dividends received from subsidiaries, joint ventures and affiliates in the "income" section of the income statement.Collaboration with data related units Information regarding transfers from the government to BUMN from the cash flow report, under "Funding Activities". Transfers from the government to BUMN and the consolidated financial statements present the value of dividends received from subsidiaries, joint ventures and affiliates in the "income" section of the income statement.Collaboration with data related units Information regarding transfers from the government to BUMN from the cash flow report, under "Funding Activities". Transfers from the government to BUMN and the consolidated financial statements present the value of dividends received from subsidiaries, joint ventures and affiliates in the "income" section of the income statement. | MSG , National Secretariat |  | 22000000 | Government Budget | bar: May IV; August III
|  | Technical Coordination about Subnational Payment (Req 4.6) and Subnational Transfer (Req 5.2) | Collaboration with units related to information on PNBP realization per region and regional retribution obtained from extractive industries | MSG , National Secretariat |  | 22000000 | Government Budget | bar: June I; September I
|  | Technical Coordination about Social Expenditure (Req. 6.1) and Environment Impact (Req 6.4) | Collaboration with units related to information data on state sales of goods and services, including volume sold and sales proceeds, disaggregated by buyer | MSG , National Secretariat |  | 22000000 | Government Budget | bar: March I; August IV
|  | Technical Coordination about Disclosure of GHG Emission from Extractive Companies (Req 3.4) | Collaboration with units related to greenhouse gas information data for extractive industry companies | MSG , National Secretariat |  | 22000000 | Government Budget | bar: April III; September III
|  | Technical Coordination related to income projections and country economic scenarios due to the energy transition (Req 5.3) | Collaboration with units related to income and economic data information for the energy transition | MSG , National Secretariat |  | 22000000 | Government Budget | bar: July I; October I
|  | Technical Coordination related to the Data Exchange Agreement and Institutional Decree of the EITI Secretariat | Collaboration with related units as a follow-up to the exchange of data and institutions of the Indonesian EITI National Secretariat | MSG , National Secretariat |  | 40000000 | Government Budget | bar: March IV; September IV
3 | Public Discussion Contribute to policy making on issues such as social and environmental spending, gender, critical minerals, pandemic recovery and anti-corruption through increased use of EITI data in public policy discussions
| a.Thematic Polic Dialog I | Using Extractive Industries Data for Better Governance and Just Energy Transition | Increasing public awareness about the benefits of extractive data portals and extractive data portal users at the regional level for better governance and a just energy transition; MSG members actively contribute to this policy dialogue by involving relevant stakeholders (academics, industry practitioners, etc.). | MSG, National Secretariat, CSO with EO Support | 2024-04-01 | 100000000 | Government Budget | bar: April IV
| b.Thematic Policy Dialog II | Using Extractive Spatial Data : Developing Story of DBH and Social Economy Impact of Extractive Sector at Subnational level | Increasing public awareness about the benefits of extractive data portals and users of extractive data portals at the regional level so that they can benefit the general public in the distribution of Sub National Transfer as well as the socio-economic impact on producing areas; MSG and CSO members actively contribute to this policy dialogue | MSG, National Secretariat, CSO with EO Support | 2024-09-01 | 100000000 | Government Budget | bar: September II
| c.Extractive Transparency Day (ETD) | Extractive Transparency Day (ETD) Event | Giving awards to companies that have participated in extractive industry transparency reporting | MSG, National Secretariat, CSO with EO Support | 2024-11-01 | 53000000 | Government Budget | bar: November III
4 | Communication Activities Strengthening the capacity of the national secretariat through the socialization of extractive data portals through business entities to support better capture of extractive portal data
| a. E-Reporting dissemination | Migas Company | Increase the participation of business entities for transparency in the extractive industry in the oil and gas sub-sector. | National Secretariat, Company | 3 times from week-3 Feb to week-4 Jun | 170000000 | Government Budget | bar: February III; May III; June IV
|  | Mining Company | Increase the participation of business entities for transparency in the extractive industry in the mineral and coal sub-sectors. | National Secretariat, Company | 3 times from week-4 Feb to week-4 Jul | 170000000 | Government Budget | bar: February IV; June II; July IV